## Cover & Instructions
KARTIFY RETAIL
STAGE 4 — INTERNAL AUDIT WORKBOOK ¦ KR-IA-001 ¦ Version 1.0
Purpose | Evidence-based testing of controls selected in the approved Statement of Applicability (Project 3).
Audit Criteria | ISO/IEC 27001:2022 + approved ISMS documents: Context of Organization, Asset Register, Risk Register, Master SoA.
Checklist Coverage | 20 audit test procedures across 12 Annex A controls, covering 10 of the 14 risks in the Master SoA (R01,R03-R10,R12).
Result Values | Conforms ¦ Observation ¦ Minor NC ¦ Major NC ¦ Not Tested
Auditor Rule | Do not mark conformity without objective evidence. Record evidence reviewed and sampling in Auditor Notes.
Finding Rule | Use a Finding ID only when a documented observation or nonconformity is raised.
Workbook Status | Completed — Final. This workbook reflects the completed Stage 4 audit; see the KR-IA-001 Internal Audit Report for full narrative, NCR field records and the Corrective Action Plan.
Next Output | Findings Register → Corrective Action Plan → Internal Audit Report (already issued as KR-IA-001).

## Audit Checklist
KARTIFY RETAIL — STAGE 4 INTERNAL AUDIT CHECKLIST
ISO/IEC 27001:2022 ¦ Audit ID KR-IA-001 ¦ Approved SoA-based testing
Test ID | Annex A | Control Name | Related Risk(s) | Asset / Audit Area | Audit Test Question | Expected Evidence | Control Owner | Result | Finding ID / Auditor Notes
IA-01 | A.5.18 | Access rights | R01 | HW-01 — AWS Production Environment | Are AWS production privileges limited to approved roles and reviewed quarterly? | AWS IAM role export; privileged-account list; quarterly access review | Head of Infrastructure | Conforms | Sampled privileged roles were approved and aligned to business need.
IA-02 | A.8.9 | Configuration management | R01 | HW-01 — AWS Production Environment | Are approved AWS configuration/security-group baselines maintained? | Configuration baseline; sampled security-group rules | Head of Infrastructure | Conforms | Sampled configurations matched approved baseline.
IA-03 | A.8.8 | Management of technical vulnerabilities | R03 | SW-01 — Marketplace Platform | Are critical/high marketplace-platform vulnerabilities remediated within defined timelines? | Vulnerability scan report; remediation tickets | Engineering Lead – Marketplace | Conforms | Remediation tickets and closure evidence available for sampled findings.
IA-04 | A.8.28 | Secure coding | R03 | SW-01 — Marketplace Platform | Are secure-coding practices and peer review applied before production release? | Pull-request samples; review approvals | Engineering Lead – Marketplace | Conforms | Sampled production-bound changes had peer review and secure-development checks.
IA-05 | A.8.24 | Use of cryptography | R04 | SW-02 — Payment Gateway Integration Module | Are TLS/tokenization cryptographic standards enforced on all payment-related endpoints? | TLS configuration scan; endpoint inventory | Engineering Lead – Payments | Nonconformity | NCR-01: one admin-facing payment-reconciliation endpoint still allowed TLS 1.1.
IA-06 | A.8.28 | Secure coding | R04 | SW-02 — Payment Gateway Integration Module | Is the payment module subject to mandatory code review and security testing before release? | Pull-request samples; security test summary | Engineering Lead – Payments | Conforms | Sampled changes had required review and automated checks.
IA-07 | A.5.15 | Access control | R05 | SW-03 — Order Mgmt & Logistics Tracking | Is access to order/delivery data restricted by role? | Access matrix; role-assignment sample | Product Owner – Logistics | Conforms | Sampled roles matched approved access matrix.
IA-08 | A.8.32 | Change management | R05 | SW-03 — Order Mgmt & Logistics Tracking | Are changes to order/dispatch logic approved, tested and traceable? | Change tickets; test evidence; deployment records | Product Owner – Logistics | Conforms | Sampled changes had approval, testing and deployment records.
IA-09 | A.5.18 | Access rights | R06 | DT-01 — Customer PII | Is customer PII access role-based and limited to minimum business need? | Access matrix; user sample | Data Protection Officer | Conforms | Sampled access matched approved roles; no excessive access identified.
IA-10 | A.8.15 | Logging | R06 | DT-01 — Customer PII | Is access to customer PII logged and available for review? | Application/database logs; log sample | Data Protection Officer | Conforms | Required access events were centrally logged.
IA-11 | A.8.24 | Use of cryptography | R07 | DT-02 — Cardholder & Payment Transaction Data | Is cardholder/payment transaction data encrypted at rest? | Encryption configuration; data-store sample | Finance Manager / PCI Compliance Lead | Conforms | Encryption settings verified on sampled data stores.
IA-12 | A.8.3 | Information access restriction | R07 | DT-02 — Cardholder & Payment Transaction Data | Is access to the Cardholder Data Environment restricted to approved roles? | CDE access list; role sample | Finance Manager / PCI Compliance Lead | Conforms | Access list matched approved CDE role list.
IA-13 | A.5.15 | Access control | R08 | DT-04 — Seller/Vendor KYC & Bank Data | Is seller KYC/bank-data access limited to current business need and adjusted after role changes? | Access matrix; role-change sample | Finance Manager | Nonconformity | NCR-02: one support-staff account retained KYC download access 60 days after a role change.
IA-14 | A.8.3 | Information access restriction | R08 | DT-04 — Seller/Vendor KYC & Bank Data | Is download/export of seller KYC documents restricted and logged? | Export logs; access list | Finance Manager | Conforms | Export actions were logged and restricted to approved roles (excluding NCR-02 account).
IA-15 | A.5.16 | Identity management | R09 | PR-01 — System Administrator | Is the joiner/mover/leaver lifecycle controlled and timely for privileged accounts? | JML procedure; lifecycle sample | Head of Infrastructure | Conforms | Sampled lifecycle events were processed within defined targets.
IA-16 | A.5.18 | Access rights | R09 | PR-01 — System Administrator | Are privileged AWS/admin accounts reviewed quarterly with management sign-off? | Quarterly access-review record | Head of Infrastructure | Observation | OBS-01: review completed, sign-off recorded 5 days after target date; no inappropriate access found.
IA-17 | A.8.32 | Change management | R10 | PR-02 — Database Administrator | Are production database changes processed through the defined change-approval workflow? | Change tickets; deployment logs | Head of Infrastructure | Nonconformity | NCR-03: one of ten sampled DB changes lacked a documented approval ticket.
IA-18 | A.8.3 | Information access restriction | R10 | PR-02 — Database Administrator | Is production database access restricted to approved DBA/service accounts? | DB ACL export; access sample | Head of Infrastructure | Conforms | Access list matched approved accounts.
IA-19 | A.5.19 | Supplier relationships | R12 | TP-02 — Payment Gateway Provider | Is payment-provider security due diligence performed and periodically reviewed? | Vendor due-diligence file; review record | Finance Manager | Conforms | Vendor due-diligence file and review record available.
IA-20 | A.5.20 | Supplier agreements | R12 | TP-02 — Payment Gateway Provider | Do supplier agreements contain appropriate security/data-protection clauses? | Supplier agreement; contract clauses | Finance Manager | Conforms | Agreement contained security, confidentiality and breach-notification provisions.

## Audit Summary
AUDIT PLAN & COVERAGE SUMMARY
Audit ID | KR-IA-001
Organization | Kartify Retail
Standard | ISO/IEC 27001:2022
Stage | Stage 4 — Internal Audit
SoA Status | Approved (Project 3 — Master Statement of Applicability)
Annex A Controls in SoA | 16
Audit Test Procedures (this cycle) | 20
Risks Covered (this cycle) | 10 of 14 (R01,R03-R10,R12)
Current Status | Completed — Final
Primary Outputs | Findings Register, Corrective Action Plan, Internal Audit Report (KR-IA-001)

## Finding Register
FINDINGS REGISTER — STAGE 4 (KR-IA-001)
Finding ID | Test ID | Annex A | Risk ID | Finding Type | Requirement / Criteria | Evidence | Condition / Finding | Risk / Impact | Corrective Action | Owner / Due Date
NCR-01 | IA-05 | A.8.24 | R04 | Nonconformity | All payment-related endpoints must enforce TLS 1.2 or higher. | TLS configuration scan of 6 payment-related endpoints. | One admin-facing payment-reconciliation endpoint still permitted TLS 1.1 cipher suites. | Increases exposure to interception/downgrade attacks; affects PCI DSS v4.0 compliance scope. | Disable legacy TLS ciphers; bring endpoint under standard hardening pipeline; re-scan all payment endpoints. | Engineering Lead – Payments / 20-Sep-2026
NCR-02 | IA-13 | A.5.15 | R08 | Nonconformity | Seller KYC/bank-data access must be reviewed and adjusted at every role change. | Access matrix review; 8-account sample. | One support-staff account retained KYC download access 60 days after a role change. | Increases risk of unauthorized disclosure of seller identity and bank account data. | Add access-review trigger to HR role-change workflow; revoke access; audit recent transfers. | Finance Manager / 15-Sep-2026
NCR-03 | IA-17 | A.8.32 | R10 | Nonconformity | All production database changes must have an associated, documented approval ticket. | Sample of 10 recent production database schema/config changes. | One of ten sampled changes was deployed without a documented change-approval ticket. | Bypasses peer review; risk to integrity of customer order and payment data. | Enforce mandatory retrospective ticketing for emergency changes within 24 hours; monthly reconciliation check. | Head of Infrastructure / 20-Sep-2026
OBS-01 | IA-16 | A.5.18 | R09 | Observation | Privileged AWS/admin accounts must be reviewed quarterly with management sign-off by the target date. | Quarterly access-review record. | Review was completed but management sign-off was recorded 5 days after the target date; no inappropriate access found. | Minor process delay; no immediate security impact identified. | Introduce automated reminders and escalation for overdue access-review sign-offs. | Head of Infrastructure / N/A