## Risk Register
Kartify Retail — Risk Register (Project 2)
Methodology: ISO/IEC 27005:2022 & NIST SP 800-30 Rev.1 ¦ Inherent Risk = Impact x Likelihood (3x3 qualitative matrix) ¦ Linked to Project 1 Asset Register
Document Owner: Head of GRC / Risk Manager ¦ Version: 1.0 ¦ Classification: Internal – Confidential ¦ Scope: India DPDP Act 2023 + PCI DSS v4.0 (cardholder data)
Risk ID | Related Asset (ID) | Threat | Vulnerability | Risk Statement | Impact | Likelihood | Inherent Risk Rating | Risk Owner
R01 | HW-01 — AWS Cloud Compute Infrastructure | External threat actor (cybercriminal) | Misconfigured AWS security groups / IAM roles exposing instances to the public internet | External threat actor could exploit misconfigured IAM permissions in the AWS cloud compute infrastructure, resulting in unauthorized access to systems storing customer PII and cardholder data, and platform-wide service disruption. | High | Medium | High | Head of Infrastructure
R02 | HW-03 — Network Firewall / VPN Gateway | External attacker | Unpatched firmware on the perimeter firewall/VPN device | An external attacker could exploit unpatched firewall firmware to bypass perimeter controls, resulting in unauthorized network access to production and payment-processing (PCI DSS CDE) systems. | High | Low | Medium | Network Security Engineer
R03 | SW-01 — E-Commerce Marketplace Platform | Cybercriminal (application-layer attacker) | Insufficient input validation / SQL injection exposure in the marketplace application code | A cybercriminal could exploit insufficient input validation in the marketplace platform, resulting in unauthorized extraction or modification of customer personal and order data. | High | Medium | High | Product Owner – Marketplace
R04 | SW-02 — Payment Gateway Integration Module | Cybercriminal (payment fraud actor) | Weak transaction validation and lack of full tokenization in the payment module | A cybercriminal could exploit weak tokenization controls in the payment gateway integration module, resulting in exposure of cardholder data and financial fraud, in breach of PCI DSS requirements. | High | Medium | High | Engineering Lead – Payments
R05 | SW-03 — Order Management & Logistics Tracking System | External attacker or malicious insider | Lack of access segmentation between order data and delivery/courier assignment modules | An external attacker or insider could exploit weak access segmentation in the logistics tracking system, resulting in unauthorized disclosure of customer delivery addresses and disruption of order fulfillment. | High | Medium | High | Product Owner – Logistics
R06 | DT-01 — Customer PII | Malicious insider or external attacker | Excessive standing access privileges and lack of data-access logging | A malicious insider or external attacker could exploit excessive, unmonitored access privileges to customer PII, resulting in unauthorized disclosure of personal data and violation of the DPDP Act 2023. | High | Medium | High | Data Protection Officer
R07 | DT-02 — Cardholder & Payment Transaction Data | External attacker (data breach actor) | Inadequate encryption of cardholder/transaction data at rest | An external attacker could exploit inadequate at-rest encryption of cardholder data, resulting in exposure of customer payment information and non-compliance with PCI DSS v4.0. | High | Low | Medium | Finance Manager / PCI Compliance Lead
R08 | DT-04 — Seller/Vendor KYC & Bank Account Data | External attacker | Weak access controls and lack of encryption on the seller onboarding portal | An external attacker could exploit weak access controls on the seller onboarding portal, resulting in exposure of seller KYC documents and bank account details, and consequent payout fraud. | High | Medium | High | Finance Manager
R09 | PR-01 — System Administrator | Malicious or compromised insider | Lack of privileged access monitoring and use of shared admin credentials | A compromised or malicious System Administrator account could exploit the lack of privileged-access monitoring, resulting in unauthorized configuration changes or data exfiltration across the production environment. | High | Low | Medium | Head of Infrastructure
R10 | PR-02 — Database Administrator | Human error | Absence of a formal change-approval process for production database changes | Human error could exploit the absence of a change-approval process for the Database Administrator role, resulting in accidental deletion or corruption of customer order and payment records. | High | Medium | High | Head of Infrastructure
R11 | TP-01 — AWS (Cloud Hosting Provider) | Vendor-side regional service disruption | Single-region hosting architecture with no documented multi-region failover/DR plan | A regional AWS service disruption could exploit the lack of a multi-region failover plan, resulting in extended platform-wide downtime for the marketplace and order fulfillment. | High | Low | Medium | Head of Infrastructure
R12 | TP-02 — Payment Gateway Provider | Third-party vendor security breach | Insufficient vendor due-diligence and absence of contractual data-protection clauses | A security breach at the third-party payment gateway provider could exploit gaps in vendor security controls, resulting in compromise of customer cardholder data processed on Kartify's behalf. | High | Medium | High | Finance Manager
R13 | TP-03 — Third-Party Logistics / Courier Partners | Vendor-side data mishandling | Courier partners store customer name, address and phone data without adequate security controls | A courier/logistics partner could mishandle customer address and contact data due to inadequate vendor-side security controls, resulting in unauthorized disclosure of customer PII and DPDP Act exposure. | Medium | Medium | Medium | Head of Logistics
R14 | HW-04 — Warehouse Barcode Scanners & Handheld Devices | Physical theft or loss | Lack of device-level encryption and remote-wipe capability on warehouse handheld devices | Theft or loss of a warehouse handheld device could exploit the lack of encryption/remote-wipe controls, resulting in exposure of cached customer order and address data. | Medium | Medium | Medium | Warehouse Operations Manager

## Risk Matrix & Legend
Inherent Risk Matrix (Impact x Likelihood) & Methodology
Impact ↓ / Likelihood → | Low | Medium | High
Low | Low | Low | Medium
Medium | Low | Medium | High
High | Medium | High | Critical
Rating |  |  |  | Definition
Low |  |  |  | Minimal harm; easily absorbed within normal operations.
Medium |  |  |  | Moderate harm; noticeable operational, financial, or compliance impact requiring management attention.
High |  |  |  | Severe harm; major regulatory (e.g., DPDP Act, PCI DSS), financial, or reputational impact, or significant service disruption.
Critical |  |  |  | Severe harm combined with high likelihood — requires immediate treatment and executive escalation.
Methodology Note |  |  |  | This register captures INHERENT risk — the risk level before existing/planned controls are factored in. A separate Residual Risk column (post-mitigation) should be added once the Risk Treatment Plan / control mapping (Project 3, Statement of Applicability) is complete, per ISO/IEC 27005:2022 §8.
Risk Statement Format |  |  |  | [Threat] could exploit [vulnerability] in [asset], resulting in [impact].
Context Reference (ISO 27001:2022 Cl.4) |  |  |  | Risk identification is scoped per Clause 4.1 (internal/external issues), Clause 4.2 (needs & expectations of interested parties — customers, sellers, RBI/DPDP regulator, PCI Council, courier partners) and Clause 4.3 (ISMS scope) established in the Kartify ISMS Scope Statement.